The Quadrangle Forest Garden project. Meeting in Shepherd’s Barn 6th Jan 2011.

Present: Alastair Mackenzie, Ayesha, Josef Davies- Coates, Jessie Teggin, Monika, Deborah Wolton.

|  | Item | Action |
| --- | --- | --- |
| 1 2. 3. 4. | Trustee’s response to the proposal and brief for Forest Garden (see e-mail Dec 2010) The business case/plan (draft) to be ready for discussion at Trustees meeting on 20th Feb 2011: What are we proposing, why, how and when. The time frame may have to be extended Trust’s offer – staying in Shepherd’s Barn, accepted and can be rolled over. All dependent on other bookings (contact Jessie). Travel expenses – a budget to be set The parts of the project: a)Initial information gathering: Regulations and permissions re: camping, planting and gas pipeline in field Suitable fruit trees and bushes for these conditions in this area Visits to local orchards and gardens Local plant/tree nurseries Insurance/public liability to cover volunteers working in the field b)The forest garden: Planting plan Time line for planting Management and maintenance schedule c) The camp site: Number and size of each pitch Car parking spaces Access (paths, tracks) Water supply and access to shower room Compost toilets Central gathering place Bonfire/BBQ sites Supply of wood Access to river, Recycling/refuse. d) The produce from the forest garden: Preserving, juicing, bottling, drying? Set up a community facility in the stables? ( see WALGA – fruit preserving equipment) e)Finding partners and volunteers f) Funding g) Education. Offering workshops/courses on Permaculture? Allocation of tasks: Project management – different tasks, timeline Field trips The Business case/plan Funding Volunteers/ partners Design Budget Regulations/permissions Logistics Simple step milestone planning Monika showed us how to approach the various tasks with a simple step by step method: Taking as an example: Preparation of the Business Case: In order to have…….(describe the outcome you want) We need to……….(brainstorm session) Prioritize the tasks Fill in a month by month time sheet with every task allocated to a month slot. | JCD, JT JT DW JT JCD,JT JT AM JT DW AM |
| 5. 6. | Priority tasks: Find out if the permaculture grant can be used for buying and planting fruit bushes (rather than trees) and for tools. Organise visits to orchards. Mark’s orchards 20th January? Visit to Wowo camp 27th Jan Find out what regulations/ permissions might be relevant to the project Next meetings: Wed. 12th Jan. to discuss project management and the business plan. At 4pm at 8 Oakford Road. Thursday 20th Jan. Visit to Mark’s orchards. (JT) Wed 26th Jan. 1st draft of design masterplan. At 8 Oakford Road 4pm. Thurs. 27th Jan. visit to Wowo camp. (AM) | AM JT AM DW JT, JC-D, DW All All All |